## Zeiten nach Tag
Datum | Von | Bis | h | Task | Bereich | 1. Woche |  | Summe | Prüfsumme h | Bereich | Task | h | Schätzung | Rechenbar | Entfallen aus Schätzung
05.05.25 | [6 empty] | 19 | 182 | 182.25 | Planung | Planung | 2.25 | 0 | -2.25 | 7
| 12:40 | 13:40 | 1 | Planung | Planung |  |  |  |  | Planung | Unterstützte Auflösungen überlegt | 1.5 | 0 | -1.5
| 16:50 | 17:35 | 0.75 | Projektsetup | Projekt |  |  | Schätzungsabweichung |  | Planung | Konzept | 0.25 | 0 | -0.25
| 20:00 | 21:00 | 1 | Title Screen | UI |  |  | -43.25 |  | Planung | Marketing | 0.75 | 0 | -0.75
06.05.25 | [9 empty] | Gameplay | Character Creation | 9.5 | 10 | 0.5
| 10:40 | 12:10 | 1.5 | Title Screen | UI |  |  |  |  | Gameplay | Checkpoints | 0.5 | 0 | -0.5
| 14:45 | 16:30 | 1.75 | Settings Saving | Technical |  |  | Monate |  | UI | Title Screen | 4.5 | 20
07.05.25 | [7 empty] | 2.75 |  | UI | Settings Screen | 4.5 | 0 | -4.5
| 10:40 | 12:10 | 1.5 | Unterstützte Auflösungen überlegt | Planung |  |  |  |  | UI | Character Creation Screen | 8.75 | 0 | -8.75
| 12:10 | 14:10 | 2 | Title Screen | UI |  |  | Soll |  | UI | Save Select Screen | 12.25 | 0 | -12.25
08.05.25 | [7 empty] | 330 |  | UI | Gameplay Screen | 1.5 | 0 | -1.5
| 9:30 | 13:00 | 3.5 | Settings Screen | UI |  |  |  |  | UI (Design) | Gameplay Screen Design | 2 | 0 | -2
| 15:45 | 16:30 | 0.75 | Planung | Planung |  |  |  |  | UI | Esc Menu | 3 | 0 | -3
| 16:30 | 18:45 | 2.25 | Character Creation Screen | UI |  |  |  |  | Technical | Settings Saving | 1.75 | 5
09.05.25 | [9 empty] | Technical | Game Saves | 8.5 | 30 | 21.5
| 10:30 | 12:45 | 2.25 | Character Creation Screen | UI |  |  |  |  | Technical | JSON Scene System | 41 | 80
| 16:20 | 17:05 | 0.75 | Character Creation Screen | UI |  |  |  |  | Technical | Applying Music Settings | 1.5 | 0 | -1.5
12.05.25 | [5 empty] | 2. Woche |  |  |  | Technical | Refactoring | 0.75 | 0 | -0.75
| 12:25 | 13:40 | 1.25 | Character Creation Screen | UI |  | 22.75 |  |  | Technical | Music Player | 9 | 0 | -9
| 14:45 | 17:00 | 2.25 | Character Creation Screen | UI |  |  |  |  | Technical | Generate Executables | 1 | 0 | -1
13.05.25 | [9 empty] | Art | Scene Graphics PoC | 0.25 | 0 | -0.25
| 10:30 | 12:30 | 2 | Game Saves | Technical |  |  |  |  | Art | Custom Font | 2.75 | 0 | -2.75
| 13:00 | 17:00 | 4 | Game Saves | Technical |  |  |  |  | Soundeffects | Gameplay Sounds | 1 | 30
14.05.25 | [9 empty] | Soundeffects | UI Sounds | 4.75 | 10
| 10:15 | 10:45 | 0.5 | Game Saves | Technical |  |  |  |  | Music | Waveform Setup | 0.75 | 0 | -0.75
| 10:45 | 13:00 | 2.25 | Save Select Screen | UI |  |  |  |  | Music | Learning Waveform | 4.25 | 0 | -4.25
| 22:05 | 23:50 | 1.75 | Save Select Screen | UI |  |  |  |  | Music | Installing Waveform Plugins | 1.75 | 0 | -1.75
15.05.25 | [9 empty] | Music | Jamming | 1 | 0 | -1
| 9:45 | 12:00 | 2.25 | Save Select Screen | UI |  |  |  |  | Music | Village Track | 23.25 | 20 | -3.25
| 21:45 | 24:00 | 2.25 | Save Select Screen | UI |  |  |  |  | Music | Respite Track | 4.25 | 0 | -4.25
17.05.25 | [9 empty] | Music | Ending Track | 0.5 | 0 | -0.5
| 11:45 | 13:00 | 1.25 | Save Select Screen | UI |  |  |  |  | Music | Ambient Creepy Track | 1.5 | 0 | -1.5
| 13:30 | 14:00 | 0.5 | Save Select Screen | UI |  |  |  |  | Writing | Supplementary Text | 1.5 | 0 | -1.5
| 17:15 | 18:45 | 1.5 | Save Select Screen | UI |  |  |  |  | Projekt | Projektsetup | 0.75 | 0 | -0.75
18.05.25 | [9 empty] | Projekt | Better Git Visualization | 0.25 | 0 | -0.25
| 11:40 | 11:55 | 0.25 | Better Git Visualization | Projekt |  |  |  |  | Projekt | Monatsretro | 0.5 | 0 | -0.5
| 11:55 | 12:25 | 0.5 | Gameplay Screen | UI |  |  |  |  | Writing | Story Planning | 12.5 | 30
| 18:15 | 18:30 | 0.25 | Scene Graphics PoC | Art |  |  |  |  | Writing | Game Text | 6 | 200
19.05.25 | [5 empty] | 3. Woche
| 10:30 | 11:30 | 1 | Settings Screen | UI |  | 13
| 11:30 | 13:00 | 1.5 | Esc Menu | UI
| 14:30 | 16:00 | 1.5 | Esc Menu | UI
| 16:00 | 17:00 | 1 | Gameplay Screen | UI
20.05.25
| 10:00 | 12:00 | 2 | Gameplay Screen Design | UI (Design)
| 12:00 | 12:30 | 0.5 | Character Creation | Gameplay
21.05.25
| 11:50 | 12:35 | 0.75 | JSON Scene System | Technical
| 15:00 | 17:30 | 2.5 | JSON Scene System | Technical
| 23:50 | 0:35 | 0.75 | JSON Scene System | Technical
23.05.25
| 14:20 | 15:20 | 1 | Game Saves | Technical
| 15:20 | 15:50 | 0.5 | JSON Scene System | Technical
26.5.25 | [5 empty] | 4. Woche
| 9:15 | 12:30 | 3.25 | JSON Scene System | Technical |  | 11.5
| 15:45 | 16:45 | 1 | JSON Scene System | Technical
27.05.25
| 18:00 | 18:45 | 0.75 | JSON Scene System | Technical
28.05.25
| 14:15 | 17:15 | 3 | JSON Scene System | Technical
| 17:20 | 18:20 | 1 | JSON Scene System | Technical
29.05.25
| 17:15 | 19:45 | 2.5 | JSON Scene System | Technical
02.06.25 | [5 empty] | 5. Woche
| 9:30 | 9:45 | 0.25 | Monatsretro | Projekt |  | 5
| 14:30 | 19:15 | 4.75 | JSON Scene System | Technical
10.06.25 | [5 empty] | 6. Woche
| 9:40 | 12:55 | 3.25 | JSON Scene System | Technical |  | 13
| 14:00 | 18:15 | 4.25 | JSON Scene System | Technical
11.06.25
| 9:55 | 11:55 | 2 | JSON Scene System | Technical
| 16:35 | 18:20 | 1.75 | JSON Scene System | Technical
| 18:20 | 19:20 | 1 | Game Saves | Technical
15.06.25
| 10:45 | 11:30 | 0.75 | Refactoring | Technical
16.06.25 | [5 empty] | 7. Woche
| 13:35 | 18:35 | 5 | JSON Scene System | Technical |  | 16.75
17.06.25
| 12:40 | 13:10 | 0.5 | Gameplay Sounds | Soundeffects
| 13:10 | 13:25 | 0.25 | UI Sounds | Soundeffects
| 15:20 | 16:05 | 0.75 | Waveform Setup | Music
18.06.25
| 18:10 | 19:25 | 1.25 | Learning Waveform | Music
| 20:55 | 22:55 | 2 | Learning Waveform | Music
19.06.25
| 9:40 | 11:40 | 2 | UI Sounds | Soundeffects
| 11:40 | 12:25 | 0.75 | JSON Scene System | Technical
| 17:50 | 18:20 | 0.5 | Gameplay Sounds | Soundeffects
| 18:20 | 18:50 | 0.5 | UI Sounds | Soundeffects
21.06.25
| 16:45 | 18:15 | 1.5 | UI Sounds | Soundeffects
| 21:00 | 21:15 | 0.25 | UI Sounds | Soundeffects
| 21:15 | 22:45 | 1.5 | Applying Music Settings | Technical
23.06.25 | [5 empty] | 8. Woche
| 9:30 | 10:00 | 0.5 | Installing Waveform Plugins | Music |  | 12.5
| 10:00 | 11:00 | 1 | Learning Waveform | Music
| 11:00 | 12:00 | 1 | Jamming | Music
| 12:00 | 12:45 | 0.75 | Installing Waveform Plugins | Music
| 17:00 | 17:30 | 0.5 | Installing Waveform Plugins | Music
| 17:30 | 18:00 | 0.5 | Village Track | Music
24.06.25
| 18:10 | 18:55 | 0.75 | Village Track | Music
26.06.25
| 9:40 | 12:40 | 3 | Village Track | Music
| 16:20 | 18:05 | 1.75 | Village Track | Music
| 22:10 | 23:40 | 1.5 | Village Track | Music
28.06.25
| 11:00 | 11:15 | 0.25 | Konzept | Planung
| 11:40 | 12:40 | 1 | Village Track | Music
30.06.25 | [5 empty] | 9. Woche
| 15:10 | 15:25 | 0.25 | Monatsretro | Projekt |  | 11.5
01.07.25
| 13:45 | 15:30 | 1.75 | Village Track | Music
| 15:30 | 16:00 | 0.5 | Ending Track | Music
| 16:00 | 18:15 | 2.25 | Village Track | Music
02.07.25
| 22:30 | 24:00 | 1.5 | Supplementary Text | Writing
03.07.25
| 12:45 | 17:00 | 4.25 | Village Track | Music
05.07.25
| 13:40 | 14:10 | 0.5 | Village Track | Music
| 14:30 | 15:00 | 0.5 | Village Track | Music
08.07.25 | [5 empty] | 10. Woche | 6.25
| 10:25 | 12:55 | 2.5 | Village Track | Music
| 21:05 | 21:35 | 0.5 | Village Track | Music
| 22:45 | 23:45 | 1 | Village Track | Music
09.07.25
| 11:15 | 12:00 | 0.75 | Respite Track | Music
10.07.25
| 10:25 | 11:55 | 1.5 | Respite Track | Music
14.07.25 | [5 empty] | 11. Woche | 9.75
| 13:00 | 13:15 | 0.25 | Respite Track | Music
| 21:00 | 22:45 | 1.75 | Respite Track | Music
15.07.25
| 10:30 | 12:00 | 1.5 | Ambient Creepy Track | Music
| 16:00 | 18:00 | 2 | Music Player | Technical
| 19:35 | 21:35 | 2 | Music Player | Technical
16.07.25
| 9:30 | 11:45 | 2.25 | Music Player | Technical
23.07.25 | [5 empty] | 12. Woche | 7.25
| 9:30 | 9:45 | 0.25 | UI Sounds | Soundeffects
| 9:45 | 11:30 | 1.75 | Music Player | Technical
24.07.25
| 9:45 | 10:45 | 1 | Music Player | Technical
| 10:45 | 12:30 | 1.75 | JSON Scene System | Technical
| 17:25 | 17:55 | 0.5 | JSON Scene System | Technical
| 20:35 | 21:35 | 1 | JSON Scene System | Technical
25.07.25
| 10:50 | 11:50 | 1 | Village Track | Music
30.07.25 | [5 empty] | 13. Woche | 3.75
| 10:25 | 10:55 | 0.5 | Village Track | Music
| 12:15 | 12:45 | 0.5 | Save Select Screen | UI
| 17:20 | 18:20 | 1 | Generate Executables | Technical
31.07.25
| 10:15 | 12:00 | 1.75 | Story Planning | Writing
04.08.25 | [5 empty] | 14. Woche | 10.75
| 9:00 | 11:00 | 2 | Story Planning | Writing
| 12:35 | 16:20 | 3.75 | Story Planning | Writing
05.08.25
| 16:05 | 17:35 | 1.5 | Story Planning | Writing
06.08.25
| 9:45 | 12:45 | 3 | Story Planning | Writing
10.08.25
| 23:00 | 23:30 | 0.5 | Character Creation | Gameplay
11.08.25 | [5 empty] | 15. Woche | 14
| 14:55 | 17:10 | 2.25 | Character Creation | Gameplay
12.08.25
| 9:55 | 11:55 | 2 | Character Creation | Gameplay
| 16:25 | 17:40 | 1.25 | Character Creation | Gameplay
| 21:30 | 24:00 | 2.5 | Character Creation | Gameplay
13.08.25
| 11:15 | 11:45 | 0.5 | Checkpoints | Gameplay
14.08.25
| 11:45 | 12:15 | 0.5 | Character Creation | Gameplay
| 12:15 | 13:15 | 1 | Custom Font | Art
| 15:15 | 18:00 | 2.75 | Game Text | Writing
| 22:00 | 23:15 | 1.25 | Game Text | Writing
2025-08-19 | [5 empty] | 16. Woche | 5.25
| 10:50 | 11:20 | 0.5 | Game Text | Writing
| 15:55 | 17:25 | 1.5 | Game Text | Writing
2025-08-20
| 22:10 | 22:40 | 0.5 | Story Planning | Writing
2025-08-21
| 21:20 | 22:35 | 1.25 | Custom Font | Art
2025-08-22
| 10:25 | 11:10 | 0.75 | Marketing | Planung
| 11:10 | 11:25 | 0.25 | Planung | Planung
| 11:25 | 11:55 | 0.5 | Custom Font | Art
2025-08-23
| 9:25 | 9:40 | 0.25 | Planung | Planung
Note on K9: -1 Monat für UGP

## Zeiten nach Aufgabe
Planung | 2 Tage nicht einberechnet weil vor Projektbeginn

## Schätzung
Bereich | Task | Schätzung in h | Zeit gebraucht | Projektsummen |  | Marketing |  | Schätzung in h | Zeit gebraucht | Gesamtsumme geschätzt | Gesamtsumme gebraucht
Music |  |  |  | Schätzung in h | Zeit gebraucht |  | Logo | 10 |  | In h | In h
| Ambient Forest Track | 10 |  | 890 | 0 |  | Website | 60 |  | 1066 | 0
| Ambient Weird Track | 15 |  |  |  |  | Online Presence | 36
| Investigation Track | 20 |  | In 6h Tagen |  |  | Trailer | 60 |  | In 6h Tagen | In 6h Tagen
| Village Track | 20 |  | 148.3333 |  |  | Demo | ??? |  | 177.6667 | 0
| Creepy Track | 20 |  |  |  |  | Send Promo Keys | 10
Soundeffects |  |  |  | In 20 Tagen Monaten |  |  | (to Reviewers & Influencers) |  |  | In 20 Tagen Monaten | In 20 Tagen Monaten
| UI Sounds | 10 |  | 7.4167 | [5 empty] | 8.8833 | 0
| Roll Reveal Sounds | 15 | [5 empty] | Summe | Summe
| Gameplay Sounds | 30 | [5 empty] | 176 | 0
| Character Sounds | 30
UI | [7 empty] | In 6h Tagen
| Text Display | 2 | 0 |  |  |  |  | 29.3333
| UI Styling | 30
| Roll Reveal Animation | 20 | [5 empty] | In 20 Tagen Monaten
| Scene Transitions | 2 | [5 empty] | 1.4667
| Special Graphical Effects | 30
| Title Screen | 20
Writing
| Story Planning | 30
| Game Text | 200
Art
| Icons & Small Graphics | 40
| ~20 Scenes | 200
| Intro Animation | ???
Content Warnings
| Research Content Warnings | 10
Technical
| JSON Scene System | 80
| Game Saves | 30
| Settings Saving | 5
Gameplay
| Ability Definition | 5
| Ability Tests | 1
| Character Creation | 10
| Moving through Scenes | 5 | 0
Note on D14: trivial, included in JSON Scene System
Note on D37: included in JSON Scene System

## Marketing
Topic | Deadline | Tasks
Firmenlogo | Oktober
Trailerplan | Oktober
Groben Spielverlauf schreiben
Beste Stellen für Trailer raussuchen
Trailermaterial | November/Dezember
Gameplay Screen UI
Animationen/Effekte für Optionen auswählen und Skilltests
Scenes für rausgesuchte Gameplay Snippets
Trailersong
Fonts für Title Cards
Webseite | Ende Jänner
Style überlegen
Evtl. Grafiken bzw. Animationen
Grundgerüst
Styling
1. Artikel
Werbematerial | Anfang Februar
Trailer fertig haben
Inhalte für Steam Page
Steam Anmeldung | Mitte Februar
UID Nummer
Steam Page | Mitte Februar
Discord Server | Ende Februar
Inhalte planen
Youtube Werbung schalten | Anfang März
Monatliche Newsletter | Beginn März?
"Doomed Herald" Konzept und Struktur ausarbeiten
Promo Orte finden @inet | Ende März
Streaming ausprobieren | April
Equipment besorgen
Streaming Software finden und lernen
Launch Trailer | Launch (September/Oktober?)
Trailer abändern lassen
Steam Keys verschicken | Launch (September/Oktober?)
Liste von Content Creatorn

## Resolutions
| Width | Height | Ratio | Img Width | Img Height | Ratios
Default | 1280 | 720 | 1.7778 | 600 | 600 | 16:9 | 1.7778
| 640 | 480 | 1.3333 | 400 | 400 | 16:10 | 1.6
[6 empty] | 4:3 | 1.3333